## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Assignee | Status
Sprint 1 | Sprint 1 | US- 1 | Project Overview | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Designing workflow and documenting project goals | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 2 | Sprint 2 | US-3 | Unit testing to ensure all intents, entities and dialogue flows are covered while ensuring proper fallback mechanisms | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 2 | Sprint 2 | US-4 | Research- going through real time applications using RASA | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 3 | Sprint 3 | US-5 | Gaining proficiency in using RASA framework | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 4 | Sprint 4 | US-6 | Gaining proficiency in using RASA framework | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 5 | Sprint 5 | US-7 | Integrating speech recognition and Language Processing | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 6 | Sprint 6 | US-8 | Workflow efficiency and Automation | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 7 | Sprint 7 | US-9 | Merging with existing services | MUST HAVE | Abhi Kavathiya | 3- Completed
Sprint 8 | Sprint 8 | US-10 | Verification and Deployment | MUST HAVE | Abhi Kavathiya | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[7 empty] | 62 | 3 | 2 | 5 | 4 | 1 | 5 | 7 | 7 | 5 | 2 | 9 | 6 | 5 | 2
SPRINT 1 BACKLOG
US - 1 | TID-01 | Project Overview and dessigning the workflow and documenting project goals | 2024-12-12 | 2024-12-15 | Individual | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US - 2 | TID-02 | Defining intents and entities | 2024-12-17 | 2024-12-21 | Individual | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US - 3 | TID-03 | Building NLU model | 2024-12-22 | 2024-12-25 | Individual | 3- Completed | 5 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US - 4 | TID-04 | Implement stories (conversational flows) | 2024-12-26 | 2024-12-30 | Individual | 3- Completed | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US - 5 | TID-05 | Implementing custom actions | 2025-01-02 | 2025-01-05 | Individual | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US - 6 | TID-06 | Integrating various apis | 2025-01-07 | 2025-01-12 | Individual | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
US - 7 | TID-07 | Improving the UI | 2025-01-14 | 2025-01-17 | Individual | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 1 | 0 | 0 | 0 | 0
US - 8 | TID-08 | Testing and Refining the responses | 2025-01-19 | 2025-01-24 | Individual | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 2 | 0
US - 9 | TID-09 | Merging with existing services | 2025-01-25 | 2025-01-29 | Individual | 3- Completed | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 3 | 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Inadequate understanding of RASA architecture and training pipelines | Participated in a detailed RASA framework workshop, reviewed official documentation, and practiced basic setup.
Sprint 2 | Day 7 | Struggled with handling NLP entities effectively | Collaborated with the mentor and implemented custom tokenization logic.
Sprint 3 | Day 12 | Structuring intents and responses | Attended sessions for the same
Sprint 4 | Day 15 | Challenges in integrating multiple APIs and dynamically redirecting them based on user needs | Implemented conditional API calls, and tested various user scenarios to ensure seamless integration.
Sprint 5 | Day 18 | Challenges in model training with large datasets, slow convergence | Optimized training scripts by incorporating batch processing and hyperparameter tuning, reducing training time.
Sprint 6 | Day 20 | Continued working on Sprint 5 | Further optimisations
Sprint 7 | Day 22 | Encountered performance issues with chatbot response time | Refined action and slot retrieval mechanisms, optimized dialogue management
Sprint 8 | Day 35 | Lack of clarity in applying TED policy for data-driven story improvisation | Took help from mentor in implementing TED Policy

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing
1 | Sprint 1 | Day 2 | Day 3 | Ayesha | Analysing and collecting requirements | Relying solely on initial assumptions | Maintaining constant communication
2 | Sprint 3 | Day 10 | Day 12 | Ayesha | Implementing initial chatbot training | Skipping documentation review | Iterating on training data
3 | Sprint 4 | Day 14 | Day 17 | Ayesha | Building API integration layer for dynamic content fetching | Overcomplicating error handling processes | Testing APIs across different environments
4 | Sprint 6 | Day 18 | Day 21 | Ayesha | Structuring dialogue management | Ignoring edge cases for user inputs | Validating edge cases in user inputs
5 | Sprint 8 | Day 35 | Day 40 | Ayesha | Exploring and integrating external APIs for advanced functionality | Relying only on internal resources | Exploring diverse options